## Slide 1: Erik’s thesis progress report
Jan 25, 2024

## Slide 2: Current Progress
Experiment almost done
    Ran AIZ with 50k chemBL molecules on ALICE using slurm
    Xgboost classification – OK results, more affected by data distribution, had to lower the number of classes
    GNN classification/regression with chemprop – more precise and promising results
    Thesis outline work in progress
    TBD:
    Error visualization
    More models?
    More data? New dataset?
    Plan a meeting with Mike

## Slide 3: To-do
Add saved train/test to xgboost
Calculate RMSE for the result vs. test / RMSE result per class vs test per class for regression (GNN)
Training/reading model shell script with chemprop commandline
Confusion matrix / F-1 score for classification

## Slide 4: Points to address
How did you create/split data set
What was the leanring task. -regression/classification
What are the Xs and Ys (f(x) = y, x= smiles, y = route length, f ~ GNN)
Describe GNN architecture in chemprop
What are the models
How do you evaluate?
HPO (built-in in chemprop)
Generalizable?
  0) remove already sampled entries
  1) Sample 5k from Chembl
  2) Inchi compare with CASPYRUS50k
  Test size ~ 1k ~5k

## Slide 5: 3-15
Universal train/test set 50k for xgB and gnn
Inference on 200k using 50k GNN model for both classification and regression (exclude duplicate from 50k training sets )
Training graph with losses
How to represent results for both algs under both test sets (80-20 50k and chemBL 200k)
  Classification Table – [accuracy, F1, MCC, precision, recall] in 1 table
  Classification plots - adjust the font size (side improvement – split the classes: 0,1,2,3,4,5+, argue about class boundary)
  Regression table – [RMSE, MAE]
  Regression plot – change scatter to box plot to show the distribution
  Presentation for Mike (to Alan first)
  Thesis structure outline first – text later

## Slide 6: Further ideas
GNN(smiles) ~ different y’s (make it plug-in and play) ()

## Slide 7: Current Progress 6-11
Experiment
    Universal train/test (80-20)
    Model save/load for both xgB and GNN
    1-click, 4 experiments with full auto graph plotting(xgB and GNN for both 1k and 50k)
    200k inference running on ALICE ongoing
    More meaningful graphs and metrics ongoing
    Thesis outline – feedback?
    Timeline discussion
      1st draft
      Presentation to Alan/Mike
      Final Draft

## Slide 8: Current Progress 6-11
      Make sure 50k aligns with 200k on AIZ configs
      Classification Table – [accuracy, F1, MCC, precision, recall] in 1 table
      The same test set for 1k and 50k (sample 1k-train from the 50k train)
      10k (in-between argument)
      Look into Alan’s cites for training scores and related articles for related work
      Start writing up to hypothesis (or summarize the general settings in methods) always bullet points first
      More structured outline
      Try finish by first week of July

## Slide 9: Current Progress 8-21
      200k solved from slurm
      Make sure 50k aligns with 200k on AIZ configs – rerun 50k on slurm if needed
      Classification Table – [accuracy, F1, MCC, precision, recall] in 1 table – can be easily made by borrowing the XGBoost result analysis calculation
        Other plots:
        Regression table – [RMSE, MAE]
        Regression plot – change scatter to box plot to show the distribution
        Loss function graph? How?
      The same test set for 1k and 50k (sample 1k-train from the 50k train) – “unified inference framework”
      10k (in-between argument) (must-have due to a discovery of lack of predictions of class 1-2 from the 1k model)
      200k Validation experiment
      Look into Alan’s cites for training scores and related articles for related work
      Start writing up to hypothesis (or summarize the general settings in methods) always bullet points first
      More structured outline
      Try finish by first week of July

## Slide 10: 8-21 meeting notes
50k result is good, test set split is not
  Redo train-test-val split, figure out a way to align xgboost with chemprop.
  Chemprop does the auto-split magic that reduces number of molecules to be used for training, try to avoid that
    Useful links:
      https://github.com/chemprop/chemprop/blob/0c4e4f36e39c647b0edf15ce15a25a0a4f4f145a/chemprop/cli/train.py#L425
      https://github.com/chemprop/chemprop/issues/639
      https://machinelearningmastery.com/avoid-overfitting-by-early-stopping-with-xgboost-in-python/
      https://chemprop.readthedocs.io/en/latest/tutorial/cli/train.html
      https://www.tensorflow.org/tensorboard
200k ultimate validation for all models and all experiment modes
    Writeup – always content first, aka graphs, cites etc, then text
      data generation – Alan’s paper explains that
  Argument about task formulation – classification >> regression
    Methodology – why trying both?
      Regression matches the chemistry intuition of how molecules grow, aka 1.7 is closer to 2 than to 1, but if using multiclass that distance can’t be told
    10k extraction from 50k – just take the top
    Graphs
      Graph format – no title, no additional metrics on graph itself (maybe only F1 for classification?)
      Loss graph – tensorboard
    tensorboard --logdir ./model_0/
      Go to the model folder of gnn, activate aizynth-dev, then we cans see all the loss graphs from tensorboard
  Classification table and Regression table that include all experiments in one graph